## Overview
The Clothing Cove — Filter & Search Readiness Plan
Make the live catalog searchable by the filters shoppers expect. Corrected June 2026 baseline (supersedes the June 10 estimate). Scope: 7709 PUBLISHED live products; ~4033 in-stock are unpublished (backlog — they become filterable as they're published).
WHERE WE STAND TODAY
Only 2 of 6 expected filters are live (Availability, Price). Brand and Garment type have data on every product but in CRYPTIC codes (supplier names like 'LEEGIN LEATHER'; 3-letter type codes like 'J E W') — they need a normalization pass before they can be enabled. Size and Color need metafield backfill; the rest are greenfield.
READINESS BY FILTER (a filter is 'fully ready' only with both the selectable option AND the taxonomy metafield that powers a clean, normalized filter)
Target filter | Scope | Fully ready | % ready | Status | Phase
Availability | 7709 | 7709 | 100% | LIVE | —
Price | 7709 | 7709 | 100% | LIVE | —
Brand | 7709 | 0 | 10% | Populated (vendor) but cryptic supplier codes — needs brand mapping | Phase 1 (normalize)
Garment type | 7709 | 0 | 10% | Populated but 3-letter type codes — needs mapping to readable types | Phase 1 (normalize)
Size | 2268 | 729 | 32.14% | Partial — backfill metafield | Phase 1
Color | 5947 | 932 | 15.67% | Partial — backfill + fill gaps | Phase 1
Fabric / Material | 1873 | 238 | 12.71% | Greenfield — proposal ready | Phase 2
Dress occasion | 1873 | 42 | 2.242% | Greenfield — via collections | Phase 2
Length | 1873 | 144 | 7.688% | Greenfield — low priority | Phase 3
Fit | 1873 | 33 | 1.762% | Not in data — capture at intake | Phase 3
THE HEADLINE: Size and Color are the conversion-critical filters. Most products already let shoppers SELECT size/color — the gap is the metafield that makes the FILTER clean and normalized. That is a structured data task done in batches, not a per-product rebuild.

## Phased Roadmap
Phased Roadmap & Timeline
Estimated effort reflects conventional, hands-on execution across the catalog (per-item work in the admin). Phased so value ships early.
Phase | Workstream | What we do | Products | Est. effort (hrs) | Timeline | Outcome for shoppers
1 | Normalize + enable Brand & Garment filters | Map supplier codes → real brand names (source: the 'Brands' collections; dedupe casing) and the 3-letter type codes → readable garment types, then enable both filters in Search & Discovery. | 7,709 | 16–26 | Weeks 1–2 | Shop by real brand name and garment type.
1 | Size backfill | Set the size taxonomy metafield on every item that already has a size selector; confirm one-size; flag true gaps. | 1,480 items | 37–62 | Weeks 1–3 | A clean, normalized Size filter.
1 | Color backfill + display | Set color-pattern on every item with a color selector; set the color filter to clean TEXT (not chips). | 2,734 items | 68–114 | Weeks 1–4 | An elevated, word-based Color filter.
2 | Fabric / Material | Read each description, assign the fabric, and set the metafield; enable the Fabric filter. | 964 items | 40–56 | Weeks 4–5 | Shop by fabric (cotton, linen, etc.).
2 | Dress occasion | Map dress sub-collections (Evening, Mother-of-Bride, Casual, Pant Sets) to occasion values; enable filter. | Dress collections | 4–8 | Week 5 | Shop dresses by occasion (wedding, work, casual).
3 | Length | Tag garment length (maxi/midi/ankle) per item where applicable; enable filter. | ~1,000 items | 25–42 | Weeks 6+ | Secondary length filter.
3 | Fit | Not present in current data — capture fit at product intake / from brand specs going forward. | Ongoing | 3–5 | Weeks 6+ | Future fit filter.
3 | Add missing size/color data (store-led) | For items with no color/size in any form, the store supplies the attributes (requires hands-on product knowledge); we provide the template, validate, and load it into the filters. | 55 size · 2,230 color | 114–171 | Ongoing | Full catalog filter coverage.
| Phase 1–2 — recommended foundation |  |  | 165–266
| Phase 3 — optional full coverage |  |  | 142–218
Hours are estimates; the recommended foundation delivers all six core filters working. Full-catalog SEO enrichment is scoped separately in the SEO & AEO Plan.

## Method & Notes
How readiness is defined, and what changed
Dual standard. A product is 'fully ready' for a filter only when it has BOTH (1) the selectable variant option shoppers pick on the product page, AND (2) the Shopify taxonomy metafield that powers a clean, normalized, swatch-or-text filter on collection pages. The option drives selection; the metafield drives a good filter.
Why the numbers changed from June 10. The first pass measured variant options only and counted any product without an exact 'Size'/'Color' option as missing. That over-counted: it ignored 'Shoe size'/'Ring size' options, items carrying the attribute in a metafield, and genuinely one-size pieces. The corrected baseline fetches the taxonomy metafields and separates true gaps from items that only need a metafield added.
Corrected size picture (scope 2,268): 729 fully ready, 1,469 need only the metafield, 55 are true gaps, 4 likely one-size.
Corrected color picture (scope 5,947): 932 fully ready, 2,734 need only the metafield, 2,230 have no color attribute at all.
Filter display
Color filters will render as clean TEXT words rather than flat color chips (a one-setting change in the theme), matching the elevated look of the site. Variant swatches on product pages are unaffected.
Data sourcing principle
No values are invented. Size/color/fabric mappings are learned from products the team already tagged; anything ambiguous is routed to a short human-review list rather than guessed. Fabric is parsed from descriptions and is therefore proposed for review before import.
Value normalization is a prerequisite, not an afterthought
The catalog currently holds ~3,620 distinct raw color strings ('BLACK 0001', 'DENIM IGNITE', 'ASST') and ~348 size strings. Filtering on raw values would produce thousands of useless, near-duplicate filter options and faceted-URL crawl traps. The backfill therefore MAPS each raw value to a normalized taxonomy value (e.g. many blues to one 'Blue' swatch) — the confident, high-frequency values are mapped automatically; the long tail of rare values is routed to human review. Filters should not be switched on until the values they expose are normalized.

## _cd
Filter | % ready
Availability | 1
Price | 1
Brand | 0
Garment type | 0
Size | 0.321
Color | 0.157
Fabric | 0.127
Occasion | 0.022
Length | 0.077
Fit | 0.018