## Proposal Summary
The Clothing Cove — Growth Proposal
SEO & AEO · Filter & Search Readiness · Projected Impact ¦ prepared June 2026
THE OPPORTUNITY
The store earns ~3,000 organic visits/month but is leaving growth on the table: the category and brand pages that should rank have no description text at all (78% of collections), so they under-perform in search and give AI nothing to read; only 2 of 6 expected filters are live; and product data isn't normalized for filtering. Sales have softened for years. The catalog is strong — discoverability and the on-site experience haven't kept up.
THE PLAN — THREE WORKSTREAMS
Workstream | What it delivers |  |  | Outcome
SEO & AEO | Write the missing content on the category and brand pages that actually drive rankings — most have no description text at all today — and make the catalog legible to AI search (schema + answer-readiness) so the store gets surfaced and cited. Product title/description cleanup is included as catalog hygiene. |  |  | Qualified traffic + AI visibility
Filter & Search | Make the live catalog filterable by the 6 core filters shoppers expect — Size, Color, Brand, Garment type (plus Price/Availability) — with clean, normalized values. |  |  | Visitors find and buy faster
Projected Impact | A measured, conservative model of the traffic and revenue lift, with monthly tracking so results are provable, not promised. |  |  | Confidence in the ROI
HEADLINE IMPACT (12 months, from 3,000 organic visits/mo)
Expected case: organic traffic ≈ +12% · revenue-per-visit ≈ +8% · combined revenue ≈ +21%. Range: +8% (conservative — for a store that's been declining, mostly stabilization) to +51% (strong). The conversion (filter) lever is the more controllable half. Revenue is an INDEX (no Orders API) — multiply by monthly revenue to dollarize. ILLUSTRATIVE, not a promise: with no Search Console/GA4 baseline yet, Phase 0 sets the real targets and re-calibrates this model.
WHAT IT TAKES TO GET THIS DONE
Foundation scope: all six core filters working + the SEO base. Three ways to deliver it — the trade-offs are time and cost.
Path | Time to complete | Cost | Trade-off
In-house (your team) | ~14–24 months (part-time) | ~$10,780–17,864 in staff wages | Pulls staff off the sales floor for a year+; historically stalls before it's finished
Outside agency | ~2–4 months | $25,625–42,000 | Specialist rates for the same hands-on, per-item work
TKBS (us) | 4 weeks | $14,000 | Same outcome — faster than in-house, a fraction of agency cost, and your team stays selling
The in-house and agency columns are what the same work costs by conventional means; TKBS delivers that scope in weeks without tying up your team.
WHAT THE $14,000 FOUNDATION COVERS
INCLUDED: Phase 0 — Search Console + GA4 connected, 16-month baseline + ranking/competitor snapshot; theme & homepage SEO — keyworded title, meta, H1, schema/OG backstop; written descriptions + SEO titles for the navigable category & brand pages (the real content gap); indexation hygiene — noindex/prune thin, empty & duplicate collections; the four core filters (Size, Color, Brand, Garment type) wired into Search & Discovery with normalized values and clean text color display (Availability + Price already on); and monthly tracking that measures the lift.
NOT INCLUDED (scoped & quoted separately, per batch): full-catalog product enrichment (custom titles, descriptions, tags & alt-text across the long tail — hygiene-level); fabric & occasion enrichment filters; reviews-app setup; and publishing/photographing the unpublished backlog.
Recommendation: start here — it delivers the diagnostics, the high-value category content, and all six core filters in ~4 weeks, with tracking that proves the lift before any full-catalog enrichment.

## Read Me
The Clothing Cove — Projected Impact
SEO / AEO / GEO + Filter & Search Readiness ¦ 12-month outlook from a 3,000 organic sessions/mo baseline
TWO LEVERS, MODELED SEPARATELY
Track A — SEO / AEO / GEO drives TRAFFIC. Optimized collection + product content, schema, and AI-answer readiness pull more organic sessions. Modeled as a cumulative lift on the 3,000/mo baseline.
Track B — Filter & Search Readiness drives CONVERSION. Color/size/material filters + on-site search help the people already arriving actually find and buy. Modeled as revenue-per-session uplift, NOT extra sessions.
WHY REVENUE IS AN INDEX, NOT DOLLARS
The Orders API was not granted (403) at audit time, so we have no baseline conversion rate or AOV. The revenue columns are indexed to 100 at today's baseline. To dollarize: multiply the index by (current monthly revenue / 100). Example: at $40,000/mo, a revenue index of 140 = ~$56,000/mo.
WHERE AEO & GEO SIT
AEO (answer engines / AI Overviews) and GEO (generative engines: ChatGPT, Perplexity, Gemini, Claude) mostly affect CITATIONS and click-through, not raw session counts — direct AI-referral traffic is still small but growing. Its measurable session contribution is folded into the upper half of the Track A band; treat raw AI-citation share as a separate KPI to watch, not a line on this chart.
SCENARIO DEFINITIONS
Conservative — partial execution. For a store that has DECLINED for years, this case is mostly STABILIZATION (arresting the slide), not net growth. SEO +5% / Filters +3% by M12.
Expected — solid execution of the category-page content + the core filters. SEO +12% / Filters +8% by M12.
Strong — category + brand/'near me' long-tail rank and the filters convert well. SEO +30% / Filters +16% by M12.
THE HEADLINE (Expected, M12): traffic ≈ +12%, revenue-per-session ≈ +8%, COMBINED revenue ≈ +21% — range +8% (conservative/stabilization) to +51% (strong). The conversion (filter) lever is the more controllable half; the traffic lever depends on rankings we have not yet baselined.
ILLUSTRATIVE — NOT A PROMISE. There is no Search Console / GA4 baseline yet, so these are scenario shapes, not committed targets. Phase 0 (connect GSC + GA4, pull a 16-month baseline) sets the real numbers; this model is re-calibrated against that data before any target is committed. SEO compounds: expect noise for 8–12 weeks.

## Projection
Projection — Sessions (Track A) & Revenue Index (Track B + Combined)
| SEO / AEO / GEO — Organic sessions/mo |  |  | Filter & Search — Revenue/session (index, base 100) |  |  | Combined revenue index (base 100)
Month | Conserv. | Expected | Strong | Conserv. | Expected | Strong | Conserv. | Expected | Strong
M0 (Jun 26) | 3000 | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
M1 (Jul) | 3000 | 3030 | 3030 | 100 | 100 | 101 | 100 | 101 | 102
M2 (Aug) | 3030 | 3060 | 3090 | 101 | 101 | 103 | 102 | 103 | 106.1
M3 (Sep) | 3030 | 3090 | 3150 | 101 | 102 | 105 | 102 | 105.1 | 110.2
M4 (Oct) | 3060 | 3120 | 3240 | 102 | 104 | 108 | 104 | 108.2 | 116.6
M5 (Nov) | 3060 | 3180 | 3360 | 102 | 105 | 110 | 104 | 111.3 | 123.2
M6 (Dec) | 3090 | 3210 | 3480 | 102 | 106 | 112 | 105.1 | 113.4 | 129.9
M7 (Jan 27) | 3090 | 3240 | 3570 | 103 | 107 | 113 | 106.1 | 115.6 | 134.5
M8 (Feb) | 3120 | 3270 | 3660 | 103 | 107 | 114 | 107.1 | 116.6 | 139.1
M9 (Mar) | 3120 | 3300 | 3750 | 103 | 108 | 115 | 107.1 | 118.8 | 143.8
M10 (Apr) | 3120 | 3330 | 3810 | 103 | 108 | 116 | 107.1 | 119.9 | 147.3
M11 (May) | 3150 | 3330 | 3870 | 103 | 108 | 116 | 108.2 | 119.9 | 149.6
M12 (Jun 27) | 3150 | 3360 | 3900 | 103 | 108 | 116 | 108.2 | 121 | 150.8
Combined index = (sessions ÷ 3,000) × (1 + filter uplift). Multiply index by (monthly revenue ÷ 100) for dollars.
Expected scenario — revenue index comparison
Month | SEO only | Filters only | Both
M0 (Jun 26) | 100 | 100 | 100
M1 (Jul) | 101 | 100 | 101
M2 (Aug) | 102 | 101 | 103
M3 (Sep) | 103 | 102 | 105.1
M4 (Oct) | 104 | 104 | 108.2
M5 (Nov) | 106 | 105 | 111.3
M6 (Dec) | 107 | 106 | 113.4
M7 (Jan 27) | 108 | 107 | 115.6
M8 (Feb) | 109 | 107 | 116.6
M9 (Mar) | 110 | 108 | 118.8
M10 (Apr) | 111 | 108 | 119.9
M11 (May) | 111 | 108 | 119.9
M12 (Jun 27) | 112 | 108 | 121